Reading Public Schools (0246)

Race to the Top (Fund Code 201) Program Narrative

- District Improvement Plan Priorities

Over the last several months, Reading Public School administrators and teacher leaders have been participating in a graduate level course in conjunction with the University of Massachusetts Lowell Graduate School of Education which has begun the process of developing professional learning communities in both our schools and our district.  As part of that process, SMART (Strategic and Specific, Measurable, Attainable, Results-Oriented, and Timebound) goals were developed to measure the success of each priority.  Each district goal will have SMART goals, each school improvement plan goal will have SMART goals, and teacher goals will have at least one department/grade level/team SMART goal.  All goals are ultimately aligned with the district goals and some of the district goals will be aligned with the state goals.

The district goals with the Superintendent’s SMART goals listed under each goal are as follows:

- Through collaboration and innovation, we will advance learning for all students by teaching and integrating 21st Century skills within a challenging standards-based curriculum.

- Increase the technology proficiency level of teachers and administrators in the school district.

- Increase student achievement in grades K-12.

- We will ensure a safe, healthy, and sustainable learning environment where all members are expected to be respectful and socially responsible.

- Decrease the number of bullying, harassment, discrimination incidents in the district.

- We will cultivate productive partnerships with families and community.

- Increase communication and collaboration with all stakeholders in the Reading Public Schools.

- Increase the revenue generation opportunities in the district.

Our priorities for our district include the following: increase college and career readiness for all students, increase effective data use, and improve teaching and learning.

- Performance Goals

Listed below are the performance goals from 2010-2014 for the Race to the Top Projects

- Increase the percentage of students who graduate from Reading Memorial High School in four years from 94.2% in 2008 to 95.8% in 2014.

- Reduce gap in high school graduation rate in four years for the following subgroups:

  - low income students from 32.5% in 2008 to 27.6% in 2014.

  - Reduce gap in high school graduation rate in four years for special education students from 14.8% in 2009 to 12.6% in 2014.

- Increase the percentage of students who enroll in college within 16 months of high school graduation from 87.8% in 2009 to 88.5% in 2014.

- Reduce gaps of students who enroll in college within 16 months of high school graduation for each low performing subgroup (2009 to 2014) by the following:

  - Low Income:  8.1% to 6.8%

  - Special Education:  22.6% to 19.2%

  - African Americans: 7.6% to 6.5%

- Increase the percentage of high school graduates who have completed the MassCore requirements from 83% in 2010 to 100% in 2014.

- Accelerate the increase in overall achievement (Grades 3-12 percentage of students who attained proficient or advanced) on the ELA MCAS from 81.6% in 2009 to 88.1% in 2014.

- Reduce achievement gaps on the ELA MCAS for each low performing subgroup, as measured by CPI by the following from 2009 to 2014.

  - Low Income:  9.5% to 7.1%

  - Special Education:  15.3% to 11.5%

  - Limited English Proficient:  10.6% to 8.0%

  - African American:  6.3% to 4.8%

  - Hispanic:  2.1% to 1.6%

- Accelerate the increase in overall achievement (Grades 3-12 percentage of students who attained proficient or advanced) on the mathematics MCAS from 76.3% in 2009 to 79.8% in 2014.

- Reduce achievement gaps for each low performing subgroup, as measured by CPI on the math MCAS by the following from 2009 to 2014.

  - Low Income:  16% to 12%

  - Special Education:  22.1% to 16.6%

  - Limited English Proficient:  8.6% to 6.4%

  - African American:  16.7% to 12.5%

  - Hispanic:  7.7% to 5.8%

In addition, the Reading Public Schools have other performance indicators that are aligned with the Race to the Top Performance Goals and the three district goals. They are listed below:

- Results on bullying questions in 2011 YRBS compared to previous years.

  - Reduce the number of students who say they are bullied by 50% (35%-H.S., 50%-M.S.)

- Increase in attendance, student achievement, high school graduation rate

  - Increase the number of students who are absent fewer than 10 days per year from 78% to 85%

  - Increase in 3-12 ELA CPI from 93.9 to 95.0.

  - Increase in 3-12 Math CPI from 90.1 to 92.0

  - Increase high school graduation rate from 93.7% to 95%

- Decrease in suspensions, expulsions, office referrals for discipline, and dropouts

  - Reduce the number of out of school suspensions from 100 to 75.

- Locally designed student survey results

  - TBD for baseline data.

- Increase in the number of teachers who are technologically proficient as measured by the DESE TSAT and the Simple K12 Assessment Tool

  - Increase number of teachers and administrators technologically proficient from 35% to 50%

- Increase in the number of teachers who have taken technology workshops in the district and conferences

  - Increase the number of teachers participating by 50%

- Increase in the number of teachers who are using Moodle in their classrooms

  - Increase from 0 teachers to 10 teachers

- Increase in the number of teachers who use web 2.0 tools in their daily teaching

  - Increase the number

- Maintain or decrease the current student to computer ratio in the district

  - Decrease from 4.1 students to computer to 3.5 students to computer

- Increase the number of students who are taking Virtual High School Courses at RMHS

  - Increase from 25 per semester to 40 per semester

- Increase the number of teachers and students in Grades 8-12 who are using the TI Inspire Graphing Calculator

  - Increase from 0% to 50%

- Increase in the number of students in Reading Enrichment Academy, RMHS summer courses, Extended Summer Programming, and Extended Day programming

  - Increase total participation levels by 10%

- Increase in the number of students participating in project based learning assignments at RMHS

  - Increase the number of students participating in project based learning by 20%

- Increase in the number of students doing Senior projects

  - Increase the number of students doing Senior projects by 20%

- Reduce achievement gaps for each low performing subgroup, as measured by CPI, by 25% on the ELA and Mathematics MCAS.

- Increase Student Achievement in MCAS

  - Increase the number of students who achieve Proficient or Advanced in ELA from 83% to 87%

  - Increase the number of students who achieve Proficient or Advanced in Math from 75% to 80%

- Increase MCAS Student Growth Percentile in mathematics and literacy

  - Increase by 5% in Grades 4-8, 10

  - Increase median SGP from 58.0 to 60.0 in ELA and 54.0 to 58.0 in Math

- Increase the number of students who fulfill the MassCORE graduation requirements at RMHS

  - From 83% to 100%

- Increase in the number of students taking AP courses at RMHS

  - Increase from 21% to 29%

- Increase the number of highly qualified teachers from 99.3% to 100%.

- Implementation Chart

The chart below describes how the three district goals and district improvement plan priorities align with the state’s and district’s goals and performance measures and with the specific Race to the Top Projects that Reading will be participating in.

Reading Public Schools:  $35,144 allocation over 4 years

Please note that no funding will be allocated from Race to the Top Funds in Year 1.

Priorities:  Increase college and career readiness for all students

Increase effective data use to improve instruction

Improve teaching and learning

| # | Required Project | District Goal | District Improvement Plan Priority | Performance Measure |
| --- | --- | --- | --- | --- |
| 1A | Implement the statewide evaluation framework | 1 | Improve teaching and learning | - Evaluation Implementation Working Group of teachers and administrators has already been established and regularly provides an ongoing review and revision of current teacher evaluation tool. (Already In Place) - Evaluation Implementation Working Group will begin assessing the similarities differences between current teacher evaluation tool and DESE regulations once they are released in 2011. (January, 2011) - Revise evaluation system once new regulations are passed. (Beginning in January, 2011) - Implement revised educator evaluation regulations by the end of SY12–13. (September, 2012) - Increase the percentage of teachers and principals who are rated as highly effective and reduce the percentage rated as ineffective throughout the grant period (specific targets to be determined once the new evaluation framework is in place) |
| 2A | Align curriculum to the Common Core State Standards | 1 | Improve teaching and learning | - Nominate members from the K-12 vertical teams for each subject area to participate in statewide meetings and trainings. (January, 2011) - Begin to review and revise existing curriculum maps based upon the Common Core State Standards (Beginning in January, 2011 and completed by June, 2012) - Begin to review and revise existing parent curriculum materials based upon the Common Core State Standards. (Beginning in January, 2011 and completed by June, 2012) - Implement the Common Core State Standards by the beginning of SY12–13. (September, 2012) |
| 2B | Strengthen climate, conditions, and school culture | 2 | Improve teaching and learning | - Participate in the Mass TeLLs survey in Spring, 2011 (Spring, 2011) - Using data from survey identify areas to address and work collaboratively to address those areas. (Dependent upon receiving of survey results) |
| 3A | Create near-real-time access to data in the Education Data Warehouse by implementing the Schools Interoperability Framework | 1 | Increase effective data use to improve instruction | - Apply for Fund Code 120 grant in Year 1 to implement SIF (January, 2011) - Once funding is secured, implement SIF (TBD) - Use the Education Data Warehouse to inform instruction, assessment, and operations by the end of SY13–14. (September, 2011) - Create near-real-time access to student data by implementing the Schools Interoperability Framework (SIF) by the end of SY13–14. (September, 2011) - Use an ESE-developed tool to evaluate the impact of at least one district professional development initiative by the end of SY13–14. (September, 2013) |
| 4A | Develop and implement a plan to increase the percentage of high school graduates completing MassCore | 1 | Increase college and career readiness for all students | - Conduct a needs assessment to determine specific areas in which existing courses or supports need to be expanded or new ones added in order to meet the targets. (January, 2011) - Identify additional resources needed to implement changes for 2011-12 school year (February, 2011) - Develop and implement a plan based upon the needs assessment. (June, 2011) |
| 5A | Implement one or more components of the statewide teaching and learning system | 1 | Improve teaching and learning | - Identify educators and contact person who will participate in the piloting of each component. (November, 2010) - Current plan is to pilot all three components for all grades, all three years. (September, 2012-June, 2014) - Use at least one component of the teaching and learning system, other than the Education Data Warehouse, by the end of SY13–14. (September 2013) |
| 2G | Support National Board of Professional Teaching Standards Certification or Recertification | 1 | Improve teaching and learning | - Identify teachers who will participate in certification process (November, 2010) - This project will be supported with local funding |
| # | Optional Projects | District Goal | District Improvement Plan Priority | Performance Measure |
| 2C | Develop experienced and effective teachers as mentors | 1 | Improve teaching and learning | - For years 2 through 4 |
| 2D | Strengthen human resource systems | 2 | Improve teaching and learning | - For years 2 through 4 - Access the HR Toolkit and DSAC HR Specialists |
| 2I | Participate in a superintendent induction program | 1 | Improve teaching and learning | - Superintendent is currently in first year of three year induction program co-sponsored with M.A.S.S. (July 2010-June, 2013) |
| 2K | Participate in National Institute for School Leadership (NISL) training for principals | 1 | Improve teaching and learning | - 6 teachers and administrators are currently taking Year 1 of the NISL training through the Northeast DSAC. They will continue into Year 2 next year. (June, 2010-September, 2012) - Identify other teachers and administrators who would be part of the next cohort. (January, 2011) |
| 2L | Access ESE-sponsored or approved professional development in priority areas | 1 | Improve teaching and learning | - Assess needs of district and have staff participate in those professional development offerings that are consistent with both local needs and the state’s Race to the Top goals. (Beginning in January, 2011) |
| 3B | Access ESE-sponsored or approved professional development on effective use of data | 1 | Increase effective data use to improve instruction | - Access free training and online training on using data to improve instruction. (Beginning in January, 2011) - Identify teacher leaders in each school who will implement the train the trainer’s model in their school. The goal is to train at least 1 teacher per team/grade level/department in each school. (Beginning in January, 2011) |
| 4B | Implement YourPlanforCollege.com: Get ready for Life After High School | 3 | Increase college and career readiness for all students | - Begin project in Year 2 |
| 5B 5C 5D | Participate in an advisory committee to develop standards based curriculum resources, extended performance tasks, or online formative and interim assessments | 1 | Improve teaching and learning | - Two teachers have applied from the district to be on advisory committees for either 5B, 5C, or 5D |

- Governance Statement

The Reading Public Schools have had a long history of collaboration between the Superintendent, the Reading School Committee, and the Reading Teacher’s Association.  One such example is the collaborative effort that was developed 7 years ago to develop a comprehensive standards-based teacher evaluation system, which has proven to be a model in the region.  That collaborative effort still occurs today as a joint committee of teachers and administrators meet quarterly to assess the current evaluation tool and to make changes where necessary.  In addition, throughout the entire Race to the Top process, there has been a very collaborative relationship between the Superintendent of Schools, the Chair of the Reading School Committee, and the President of the Reading Teacher’s Association.  As part of this process, presentations and dialogue about the process and the plan have occurred with both the Reading School Committee and the Reading Teachers Association Executive Board.  The final plan that will be submitted to DESE by October 22nd has been shared with both the Reading School Committee, the Chair of the Reading School Committee, the Reading Teachers Association Executive Board, and the President of the Reading Teacher’s Association.  Public presentations and discussions have occurred as a result of the process.  The Reading School Committee Chair, Superintendent of Schools, and President of the Reading Teacher’s Association will receive a copy of the RFP and the entire district response.