Reading public Schools

District Improvement Plan 2020-2023 School Years Superintendent’s Educator Plan 2020-21 School Year

DRAFT

John F. Doherty, Ed.D.

10/29/2020

Reading Public Schools District Improvement Plan

Strategy and Goals for Improvement of Student Outcomes (2020-2023 School Years)

| Our Mission |  |  |  |
| --- | --- | --- | --- |
| Instilling a joy of learning and inspiring the innovative leaders of tomorrow |  |  |  |
| Our Vision |  |  |  |
| It is the vision of the Reading Public Schools to instill a joy of learning by inspiring, engaging and supporting our youth to become the innovative leaders of tomorrow. We will accomplish our vision by focusing on a few key strategic initiatives that lead to a meaningful and relevant curriculum, innovative instructional practices, strong analysis and thoughtful dialogue about evidence, a collaborative and team approach to learning and teaching, and a safe and nurturing learning environment. The overall physical and behavioral well-being of our children will be our top priority as students will not learn if they are not physically and psychologically safe. Education will truly be the shared responsibility of both the schools and the community, with families playing active roles in the schools and being full partners in ensuring the success of their children. In the interest of the entire Reading community, the school district and town government shall work cooperatively and collaboratively. As educators and members of our community, we believe that implementing this vision is our ethical responsibility to the children of the Town of Reading. |  |  |  |
| Our Theory of Action |  |  |  |
| If the Reading Public School District strategically allocates its human and financial resources to support high quality teaching, prioritizes a commitment to the academic, social, and emotional needs of our students, emphasizes the hiring and support of effective staff who have the capacity to collaboratively learn, thoughtfully analyzes measurements of school performance and provides differentiated support, then students will make effective progress and be appropriately challenged, graduating from high school ready for college, career, and life as contributing citizens in a global society. |  |  |  |
| Strategic Objectives |  |  |  |
| Strategic Objective A Redesigning School (2020-2021 School Year) Based on our work since March, 2020, the school district will build a foundation of teaching and learning practices, infrastructure changes, assessment practices, and operations efficiencies to prepare schools for current conditions and future challenges in a post-pandemic world. | Strategic Objective B Coherent Instructional Systems (2020-2023 School Years) Based on qualitative and quantitative data analysis, the school district will evaluate and refine standards-based instructional systems to meet the needs of all learners. | Strategic Objective C Supportive and Safe Learning Environment (2020-2023 School Years) Based on quantitative and qualitative data analysis, the school district will review our equity and social justice practices, analyze student social emotional growth, and refine systems of support to ensure a healthy and successful learning community while meeting the unique needs of students. |
| Strategic Initiatives |  |  |
| - Develop Fall Reopening Plan for School District which adheres to DESE, DPH, and CDC regulations. - Implement Fall Reopening Plan which includes the following: - Procurement of appropriate PPE, Technology, Online Curriculum, and Professional Development - Addressing the foundation needs (laptops, wireless hotspots, food insecurities) of all students - Supporting the Social and Emotional Learning needs of students and staff - Proper cleaning, disinfecting, and maintaining of HVAC systems according to industry standards - Following proper health and safety guidelines - Continue to strengthen remote learning practices with staff and students. - Practice flexibility when phasing from one model to another. - Identify assessments for both in person and remote learning that will be used for analysis and select district baseline data to establish targets for improvement for future years. - Implement a continuous student support cycle: identify at risk students, select evidence-based interventions, enact interventions, and monitor student progress/growth. - Continue NEASC work at RMHS - Work with stakeholders to develop a vision of the graduate (May, 2021). | - Continue implementation of a five-year curriculum overview and examination cycle in all curriculum areas with adjustments made, if necessary, on an 8 year cycle. - Develop and implement a five-year special education program review cycle. - Develop entrance and exit criteria for students entering district special education programs as appropriate. - Completion of curriculum guides, PreK-12. - Complete implementation of social studies curriculum standards. - Review and pilot curriculum material in Grade 6 mathematics. - Commit resources to focused and aligned professional development opportunities on meeting the needs of diverse learners for administrators, teachers and support staff. - Implement Universal Design for Learning across the school district. - Work with TAP Committee to review new teacher evaluation rubrics for implementation in 2021-2022 school year. - Select and implement a high-quality universal screening assessment for K-5 students. - Using DESE guidelines develop and implement a process on Early Literacy Screening. - Implement revised elementary standards-based report card. - Develop and implement a plan to improve early literacy skills, K-3. | - Conduct an equity audit of the school district. Using the results of the audit, an action plan will be developed. - Use the DESE Safe and Supportive Schools Framework and Tool to assess the district and schools from this lens. - Complete PK-12 SEL curriculum guides. - Align K-5 SEL report card standards. - Provide Professional development in SEL, trauma, equity and diversity. - Develop student programs that focus on equity and diversity. - Develop plan for family and community awareness and engagement of SEL standards and practices. - Revise middle school and high school handbooks to reflect updated policies and equity practices. - Develop an explicit decision-making process for determining student access to Tier 2/3 interventions for behavioral health (IP) - Build a more supportive school climate (PBIS) to reduce the use of exclusionary discipline while promoting a supportive school culture (restorative practices) - Develop and implement a plan to recruit, select, and retain a diverse workforce in the school district. - Develop a leadership academy for aspiring school leaders. - Work with public safety to review efficacy and implementation of all safety drills. - Continue elementary space needs and enrollment study and prepare recommendations to the School Committee and Community for approval. - Work with Town Manager to continue to develop a capital plan that focuses on health and safety issues. |
| Interim Outcomes |  |  |
| - Based on baseline data from the 2020-2021 school year, there will be 2% increases in state assessment results in Grades 3-8, 9, and 10 by cohort from Year 1 to Year 2 and Year 2 to Year 3. - Based on baseline data from 2020-2021 school year, there will be 2% increases in identified local assessments in Grades 1-5 by cohort from Year 1 to Year 2 and Year 2 to Year 3. - Based on baseline data from 2020-2021 school year, there will be 2% increases per surveyed grade in the student learning environment scores as evidenced by the PRIDE survey, MCAS survey, and other student climate data from Year 1 to Year 2 and Year 2 to Year 3. - Based on baseline data from the 2020-2021 school year, there will be 2.5% increases in % student participation from Year 1 to Year 2 and Year 2 to Year 3 in AP Exams and an increase in participation of 5% from Year 1 to Year 2 and Year 2 to Year 3 of students of color. - Develop/Identify one common district assessment at each grade level (K-8) per subject area at the end of Year 1 and begin implementation of assessments in Year 2. - During the 2020-2021 school year, 5 percent of our teacher interviewees will identify as people of color, 7.5 percent in 2021-22 school year, and 10 percent in the 2022-23 school year. |  |  |
| Final Outcomes |  |  |
| - During the 2020-2021 School Year, we will measure the success of our hybrid/remote learning by surveying and conducting focus groups with parents, students, and staff. - During the 2020-2021 School Year, we will maintain an average of 90% engagement by level on remote learning as measured by daily attendance. - From the 2020-2021 school year to the 2022-2023 school year, there will be a decrease in the achievement gap by 10% on state and local assessments between high needs subgroup (special education, English Language learners, and economically disadvantaged) and the general population of students. As a baseline use the 2020-2021 data. - An improvement of 5% in state and local assessments including Next Generation MCAS state assessments (% meeting/exceeding and growth), SAT scores (using 2020 as baseline), AP Scores (% student participation and scores), and local assessments. - An 10% increase of cohorts of students reaching expected benchmarks on the K-2 AMC assessment. - From the 2020-2021 school year to the 2022-2023 school year, there will be an increase of 5% positive overall response in student learning environment scores (school life) as evidenced by the PRIDE student survey and other student data. - From the 2020-2021 school year to the 2022-23 school year, there will be an increase of 5% positive overall response in school leadership, shared decision-making, and school climate as evidenced by the PRIDE staff survey. - By December, 2020, the following will be completed: publishing of Curriculum Guides in all grades/major subjects; creation of Centralized Teacher Resources with curriculum resources including but, not limited to planning materials, pacing guides, common assessments and learning progressions. - By December, 2020, there will be a five year cycle for special education program review. - By December, 2020, there will be program descriptions for each special education program with entrance and exit criteria for some programs. - By, Fall, 2021, the capital project for school security will be completed and there will be updated safety drills and protocols in collaboration with public safety. - By, June, 2023, decisions will be made on the elementary space needs and enrollment study. - By May, 2021 a vision of the graduate for the Reading Public Schools will be approved by the Reading School Committee. - In the 2022-2023 school year, we will retain 90% of our staff of color. - By the Fall, 2023, all schools and the district will be designated as “Substantial Progress Towards Targets” or greater on the current Massachusetts State Accountability System. |  |  |

Superintendent’s Goals

Goal #1-Professional Practice Goal (Aligned with Strategic Objective C)

During the 2020-21 school year, the Reading Public Schools will begin a three-year plan to develop and implement a talent diversification and leadership development strategy. The success of this plan will be evidenced by an increase in pipeline development, recruitment, and retention of staff of color.  Through the implementation of this plan, we will see an increase in staff of color by 100% (6 to 12) by the end of the 2022-23 school year.

| Goal 1-Professional Practice Goal: Planned Activities Describe actions the educator will take to attain the professional practice goal. Activities may apply to individual and/or team. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Supports/Resources from School/District1 | Lead | Timeline or Frequency | Status |
| - Hire a Human Resources Director - Create a diversity hiring committee consisting of teachers, paraeducators, and administrators. - Develop a value proposition for potential staff of color. The value proposition is a set of attributes that candidates and employees perceive as the value they gain through employment in an organization. These include tangibles (benefits, compensation, career pathways) and intangibles (culture, support, system, and mission). - Conduct an internal audit of our current talent management process which includes an assessment of diversification for pipeline development, recruitment, and retention. - Pipeline Development - Increase the number of student teachers in the district and student teachers who are individuals of color, PreK-12. - Increase the number of paraeducators in our district who are individuals of color. - Provide paraeducators with Bachelor’s Degrees access to teacher preparation professional development. - Develop education coursework for Seniors who may be interested in pursuing a teaching degree. - Recruitment - Prioritize recruitment through Linkedin, Talent Ed, Indeed, and other recruiting websites. - Audit all recruitment materials, including the website, job descriptions, and job postings to ensure the district’s commitment to diversity is clearly communicated. - Identify and participate in job fairs that focus on recruiting teachers of color. - Retention - Conduct qualitative data gathering through surveys or focus groups with teachers of color to ensure that they feel valued. - Use the educator evaluation process and the mentor program to support teachers progress. - Publicly recognize teachers. - Based on the audit, adjust our talent practices and create a long-term diversification strategy. - Develop an Aspiring Leadership Program for Teachers. | FY21 Operating Budget Meeting Time Meeting Time Meeting Time Professional Development Funds High School Coursework Reallocation Recruitment Funding for Services Time Recruitment Funding for Services Time Time Time Time FY22 or FY23 Funding | Superintendent Superintendent Diversity Hiring Committee HR Director Diversity Hiring Committee Principals Principals Assistant Superintendent High School Principal HR Director HR Director HR Director Principals HR Director Principals HR Director Superintendent Superintendent | December, 2020 February, 2021 March, 2021 March, 2021 January, 2021 September, 2021 September, 2021 September, 2021 September, 2021 March, 2021 January, 2021 March, 2021 March, 2021 Weekly June, 2021 June, 2021 June, 2022 | In Process Planned Planned Planned Planned Planned Planned Planned Planned Planned Planned Planned Ongoing Planned Planned Planned |

Goal #2-Professional Practice Goal (Aligned with Strategic Objective B)

During the 2020-2023 School Years, we will improve our literacy evaluation process, enhance our reading instructional strategies, and structure our progress monitoring more effectively for students who are struggling readers.  Based on our work, we will see progress as evidenced by reviewing previous case studies of students who struggled with Tier 2 interventions and comparing the following: an increase in identifying struggling readers earlier, students demonstrating growth on their IEP literacy goals, and fewer out of district placements with specific learning disabilities.

| Goal 2-Professional Practice Goal: Planned Activities Describe actions the educator will take to attain the professional practice goal(s). Activities may apply to individual and/or team. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Supports/Resources from School/District | Lead | Timeline or Frequency | Status |
| - Training with Dr. Orkin and Crafting Minds for Team Chairs and School Psychologists, Reading Specialists, Special Education and Curriculum Administration and selected principals consisting of: - Professional development virtual workshops regarding characterization, morphology, categorization, executive functioning, and using learning standard entry points. - Developing a consistent battery of sensitive reading assessments for initial evaluations & reevaluations to target specific areas of reading (i.e., phonological awareness, decoding, fluency, comprehension, vocabulary) & use results to drive specific reading instruction - Select and implement a high-quality universal screening assessment for K-5 students. - Using DESE guidelines develop and implement a process on Early Literacy Screening. - Determine & implement consistent progress monitoring practices for various specialized reading instructional practices (i.e., phonological awareness, decoding, fluency, comprehension, vocabulary). - Identify specific reading benchmark assessments to be given 2-3 times a year & train staff how to administer the benchmark assessments for the Bridge program. - Coach staff to chart & share progress with families & use it to drive instructional practices - Initial Training in early literacy as part of the Crafting Minds Training of Sped Teachers, Reading Specialists, SLPs, School Psychologists, Team Chairs, Principals, and Administrators. It introduces the subtypes frameworks, related assessments, and works through case studies. In addition, there is a module that addresses Orthographic Mapping and trains participants in the use of the phonological awareness screening test (PAST) and instructional routines to build students' sight word recognition. - Order Reading materials to ensure that appropriate target instructional practices are utilized at every level. - Provide appropriate training to staff in how to implement new reading programs and assessments. - Work with the District SEPAC to develop parent trainings in the basics of reading. - Implement an evaluation protocol based on the Crafting Minds training to be completed by the special education team when a specific learning disability in the area of reading is suspected or part of a three year re-evaluation. - Hire a Special Education Literacy Coach which will be focused on improving reading practices in all special education programs and settings. - Implementation & Coaching with Crafting Minds – In the second year staff examine the use and familiarity with key assessments (addition training is available as necessary in the administration and interpretation of the CTOPP, RAN, TOWRE & GORT). School-based coaching will also be provided to support the use of the graphic organizer for newly assessed and existing students with reading goals. Coaching can extend into instruction. One key goal of this year is to collect school-based and district-wide data regarding the subtypes of student with reading goals in order to make data-driven decisions when investing in curricula, training, and supplemental resources. - Sustainability & Connecting to General Education with Crafting Minds - Over the course of the third year responsibility for interpretation will be released to teams. General Educators will receive training in common learning profiles, needs, and accommodations/modifications for students with reading goals. Ongoing coaching for those delivering small group and specialized instruction as necessary. - Communicate updates regularly via meetings and newsletters. | FY20 Budget FY21 Budget FY21 Budget Inservice Time In service Time In service Time FY21 Budget and Grants FY21 Budget and Grants FY21 Budget and Grants In Service In Service FY22 Budget FY22 Budget and Grant Funding FY23 Budget and Grant Funding School Committee and SEPAC Meetings | Director of Student Services Assistant Director of Student Services Assistant Superintendent Assistant Superintendent Assistant Superintendent Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services Director of Student Services | June, 2020 December, 2020 June, 2021 2020-2021 School Year 2020-2021 School Year 2020-2021 School Year 2020-2021 School Year 2020-2021 school year 2020-2021 school year 2019-2020 and 2020-2021 school years 2020-2021 school year Pending SC and TM approval, 2021-2022 school year. 2021-2022 School Year 2022-2023 School Year Ongoing | Completed In Process Planned In Process In Process In Process In Process Planned Planned Planned Planned Planned Planned Planned In Process |

Goal #3-District Vision of the Graduate (Aligned with Strategic Objective A)-Over the next school year, I will work with Reading educators, parents, local officials and community members to learn about and develop a vision of what skills, knowledge, and dispositions Reading students should attain and develop during their preK-12 years in our schools.  Through these conversations, we will develop and receive approval of a district vision of the graduate which will be used as a vision statement for the Reading Public Schools and for the NEASC Accreditation Process.

Essentially, we will ask our stakeholders these three questions:

- What are the hopes, aspirations, and dreams that our community has for our young people?

- What are the skills and habits of mind that our children need for success in this rapidly changing and complex world?

- What are the implications for the learning experiences we provide in our school systems?

| Goal 3-Professional Practice Goal: Planned Activities Describe actions the educator will take to attain the professional practice goal(s). Activities may apply to individual and/or team. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Supports/Resources from School/District | Lead | Timeline or Frequency | Status |
| - Build understanding and ownership among district’s leadership team, School Committee, and Community as to the need and sense of urgency in this activity. - Create a Vision of a Graduate Design Team from all sectors and stakeholders that will be involved across all phases to build a sense of urgency and create excitement across the community - Define the overall timeline - Convene the VOG Design Team - Study the implications for your students in light of the changing economy, workplace, and society - Draft a prioritized set of competencies, including 21st century skills, mindsets, and literacies - Draft visuals that convey a compelling story - Reach consensus about a selected visual to share with the broader community - Continue to discuss this work in the broader community and elicit their ideas for the Vision - Collect feedback from the community and share with the Vision Design Team as they draft the Vision - Decide what revisions are necessary - Submit recommendation to the School Committee for approval - Publish and leverage the adopted Vision as the Compass for the development of the district improvement plan, RMHS NEASC visit and the design of educational experiences for students | Meeting Time Meeting Time Time Time Meeting time for VOG Design Team Meeting time for VOG Design Team Meeting time for VOG Design Team Meeting time for VOG Design Team Community Meeting Times Community Meeting Times Meeting time for VOG Design Team Meeting Time Time | Superintendent High School Principal Superintendent High School Principal Superintendent High School Principal Superintendent High School Principal VOG Design Team VOG Design Team VOG Design Team VOG Design Team VOG Design Team VOG Design Team VOG Design Team VOG Design Team Superintendent of Schools | November, 2019-January, 2020 November, 2019-January, 2020 November, 2019-January, 2020 February-April, 2020 November, 2020-February, 2021 November, 2020-February, 2021 November, 2020-February, 2021 February/March, 2021 March, 2021 March, 2021 March, 2021 April, 2021 April, 2021 | Complete Complete Complete Complete Planned Planned Planned Planned Planned Planned Planned Planned Planned |

Goal #4-School Physical and Psychological Safety (Aligned with Strategic Objective C)-During the 2020-2021 school year, we will continue to build and implement an infrastructure and a set of policies and procedures that will support the physical and psychological safety of our staff and students.  The evidence to support a successful completion of this goal will be a positive response in the 2020-2021 staff survey of PRIDE in related attributes and a positive response in the student climate survey of the YRBS and DESE Climate Survey.

| Goal 4-Professional Practice Goal: Planned Activities Describe actions the educator will take to attain the professional practice goal(s). Activities may apply to individual and/or team. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action | Supports/Resources from School/District | Lead | Timeline or Frequency | Status |
| - Develop a District Wide Safety and Crisis Committee which will include teachers, building level and central office administrators, and public safety. - Develop and implement protocols for COVID-19 Infections in the schools. - Complete MOU with Reading Police Department - Work with Public Safety to review drills and drill schedule during pandemic to assess effectiveness and impact on student social and emotional needs. - Facilities Department develops a cleaning/disinfecting protocol and ongoing ventilation maintenance program which includes, but is not limited to installation of MERV-13 filters, misting disinfecting, installation of lexan shields, floor markings, and daily cleaning/disinfecting of all areas. - Provide Professional development in SEL, trauma, equity and diversity. - Complete Safety and Security Project | Time Time Student Services Legal Counsel Time FY21 Budget and Grants Inservice Time FY21 Budget and Grants Donations Capital Funding | CFO Director of Student Services Superintendent Director of Nurses Superintendent Police Chief Superintendent CFO Police Chief Fire Chief CFO Director of Facilities Assistant Superintendent CFO Director of Facilities | March, 2020 Ongoing August, 2020 2020-2021 School Year 2020-2021 School Year 2020-2021 School Year November, 2021 | Complete In Process Complete In Process Ongoing In Process In Process |

Must identify means for educator to receive feedback for improvement per 603 CMR 35.06(3)(d).

Must identify means for educator to receive feedback for improvement per 603 CMR 35.06(3)(d).

Must identify means for educator to receive feedback for improvement per 603 CMR 35.06(3)(d).